## Light
Prediction on Loyal Customer
MLT2-DTS 2022 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Group FIN_2
Project Start Date: | 2022-07-17 |  |  |  |  | July | [20 empty] | August | [27 empty] | September
Scrolling Increment: | 0 | time axis 2022-07-17 to 2022-09-10
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-07-17 to 2022-09-10
Creating Proposal
Brainstorming Proposal | Milestone | Candra, Dimas & Dhian | 25% | 2022-07-17 | 1 | bar: 2022-07-17
Dividing Task making Proposal | On Track | Candra, Dimas & Dhian | 25% | 2022-07-18 | 1
Creating Proposal | Med Risk | Candra, Dimas & Dhian | 50% | 2022-07-19 | 1
Collect our Proposal in a docx | Goal | Candra, Dimas & Dhian | 100% | 2022-07-20 | 1 | 2022-07-20: 2
Code the machine learning project
Brainstorming our dataset | Milestone | Candra, Dimas & Dhian | 10% | 2022-07-21 | 1 | bar: 2022-07-21
Load the train and test data | Low Risk | Candra, Dimas & Dhian | 10% | 2022-07-21 | 7
Define the keras model | Med Risk | Candra, Dimas & Dhian | 30% | 2022-07-22 | 6
Compile Keras Model | Med Risk | Candra, Dimas & Dhian | 10% | 2022-07-23 | 5
Fit Keras Model | Med Risk | Candra, Dimas & Dhian | 20% | 2022-07-24 | 4
Evaluate Keras Model | Med Risk | Candra, Dimas & Dhian | 20% | 2022-07-25 | 3
Make a Predictions | Goal | Candra, Dimas & Dhian | 100% | 2022-07-26 | 2 | 2022-07-26: 2; 2022-07-27: 2
Making the Video Proposal
Record video Presentation | Low Risk | Candra, Dimas & Dhian | 50% | 2022-07-25 | 2
Upload our video | Goal | Candra, Dimas & Dhian | 100% | 2022-07-26 | 2 | 2022-07-26: 2; 2022-07-27: 2
Github repo & Documentation
Create the repo & Upload the codes | Low Risk | Candra, Dimas & Dhian | 100% | 2022-07-17 | 7
making the Final Documentation | Goal | Candra, Dimas & Dhian | 100% | 2022-07-21 | 7 | 2022-07-21: 2; 2022-07-22: 2; 2022-07-23: 2; 2022-07-24: 2; 2022-07-25: 2; 2022-07-26: 2; 2022-07-27: 2
To add more data, Insert new rows ABOVE this one